SOFTWARE PROJECT MANAGEMENT PLAN

FOR

WEB-BASED TRACKING SYSTEM FOR CTIS ALUMNI

TEAM 19

Acquirer			:	Ayşin Solak ÖRKÇÜOĞLU

Team Members	:	Bengü KARAKOÇ

Bora KORKMAZ

Burçak AYDIN

Gizem SELEK

Due Date			:	November 28, 2008

Table of Contents

1	Overview	7

1.1	Project Summary	7

1.1.1	Purpose, scope, and objectives	7

1.1.2	Assumptions and Constraints	8

1.1.3	Project Deliverables	9

1.1.4	Schedule and Budget Summary	11

1.2	Evolution of the SPMP	11

2	References	12

Book, Documents	12

Web References	12

3	Definitions and Abbreviations	12

Definitions	12

Abbreviations	13

4	Project Organization	14

4.1	External Interfaces	14

4.2	Internal Interfaces	15

4.3	Roles and Responsibilities	16

5	Managerial process plans	18

5.1	Project Start-up Plan	18

5.1.1	Estimation Plan	18

5.1.2	Staffing Plan	21

5.1.3	Resource acquisition plan	23

5.1.4	Project staff training plan	23

5.2	Work plan	24

5.2.1	Work activities	24

5.2.2	Schedule allocation	45

5.2.3	Resource allocation	47

5.2.4	Budget allocation	48

5.3	Control plan	49

5.3.1	Requirements control plan	49

5.3.2	Schedule control plan	49

5.3.3	Budget control plan	50

5.3.4	Quality control plan	50

5.3.5	Reporting plan	50

5.3.6	Metrics Collection Plan	51

5.4	Risk management plan	52

5.5	Project closeout plan	53

6	Technical process plans	53

6.1	Process model	53

6.2	Methods, tools, and techniques	55

6.3	Infrastructure plan	56

6.4	Product acceptance plan	57

7	Supporting process plans	58

7.1	Configuration management plan	58

7.2	Verification and Validation	59

7.3	Documentation Plan	60

7.4	Quality Assurance Plan	61

7.5	Review and audits plan	62

7.6	Problem resolution plan	63

7.7	Subcontractor management plans	64

7.8	Process improvement plan	64

8	Appendices	65

8.1	Appendix A	65

8.2	Appendix B	66

List of Tables

Table 1 Project Deliverables	9

Table 2 : SPMP Evolution	10

Table 3 Abbrevations	12

Table 4 : Roles	15

Table 5 : Team Roles and Responsibilities	16

Table 6 : ILF, EIF, EI, EO and EQ	17

Table 7 : Unadjusted Function Point	18

Table 8 : Staff Planning	21

Table 9 :  Staff Training Plan Table	22

Table 10 : Work Package Specification (Activity 1.1)	23

Table 11 : Work Package Specification (Activity 1.2)	24

Table 12 : Work Package Specification (Activity 1.2.1)	24

Table 13 : Work Package Specification (Activity 1.2.2)	25

Table 14 : Work Package Specification (Activity 1.2.3)	25

Table 15 : Package Specification (Activity 1.3.1)	26

Table 16 : Work Package Specification (Activity 1.3.2)	26

Table 17 : Work Package Specification (Activity 1.3.3)	27

Table 18 : Work Package Specification (Activity 1.3.4)	27

Table 19 : Work Package Specification (Activity 1.3.5)	28

Table 20 : Work Package Specification (Activity 1.3.6)	28

Table 21 : Work Package Specification (Activity 1.4.1)	29

Table 22 : Work Package Specification (Activity 1.4.2)	29

Table 23 : Work Package Specification (Activity 1.4.3)	29

Table 24 : Work Package Specification (Activity 1.4.4)	30

Table 25 : Work Package Specification (Activity 1.4.5)	30

Table 26 : Work Package Specification (Activity 1.4.6)	31

Table 27 : Work Package Specification (Activity 1.4.7)	31

Table 28 : Work Package Specification (Activity 1.4.7)	32

Table 29 : Work Package Specification (Activity 1.5)	32

Table 30 : Work Package Specification (Activity 1.5.1.1)	33

Table 31 : Work Package Specification (Activity 1.5.1.2)	33

Table 32 : Work Package Specification (Activity 1.5.2)	34

Table 33 : Work Package Specification (Activity 1.5.3)	35

Table 34 : Work Package Specification (Activity 1.5.4)	35

Table 35 : Work Package Specification (Activity 1.5.5)	36

Table 36 : Work Package Specification (Activity 1.6.1)	36

Table 37 : Work Package Specification (Activity 1.6.2)	36

Table 38 : Work Package Specification (Activity 1.6.2.1)	37

Table 39 : Work Package Specification (Activity 1.6.2.2)	37

Table 40 : Work Package Specification (Activity 1.6.2.3)	38

Table 41 : Work Package Specification (Activity 1.6.2.4)	38

Table 42 : Work Package Specification (Activity 1.6.3)	39

Table 43 : Package Specification (Activity 1.6.4)	39

Table 44 : Work Package Specification (Activity 1.6.5)	40

Table 45 : Work Package Specification (Activity 1.7.1)	40

Table 46 : Work Package Specification (Activity 1.7.2.1)	41

Table 47 : Work Package Specification (Activity 1.7.2.2)	41

Table 48 : Work Package Specification (Activity 1.7.2.3)	42

Table 49 : Work Package Specification (Activity 1.7.2.4)	42

Table 50 : Work Package Specification (Activity 1.8.1)	43

Table 51 : Package Specification (Activity 1.8.3)	43

Table 52 : Schedule of Work Activities and Milestones	46

Table 53 : Resource Allocation	47

Table 54 : Metrics Collection	50

Table 56 : Quality Assurance Items	60

List of Figures

Figure 1 : External Interfaces	13

Figure 2 : Internal Structure	14

Figure 3 : Process Model	52

Figure 4 : Gantt Chart-1	64

Figure 5 : Gantt Chart-2	65

Change History

| Date | Version | File Name | Document Format | Status |
| --- | --- | --- | --- | --- |
| 28/11/2008 | 1.0 | Team19_SPMP_v1.0en.doc | MS Word | Created |

Preface:

This document contains Software Project Management Plan for the Web-based tracking system for CTIS Alumni. This document is prepared according to the “IEEE Standard for Software Management Plans (1058-1998)”.

This document includes the project plans, for example; external and internal interfaces in the organization, the roles and responsibilities, and managerial process plan such as estimation plan, staffing plan, and project staff training plan. Cost and effort estimations that will be calculated, may lead us any updates that will be applied on these calculations in future documentations.

In software engineering, a web-based system is an application and it is accessible via web browser. Also this product is a web-based program and in this product web-based system will allow the users to have their own profiles and personal data.

# Overview

## Project Summary

Web-based Tracking System for CTIS Alumni provides tracking of its students after their graduation. Alumnus fills individual information in the form which is given by department of CTIS. Their information’s are forwarded to authorize and also authorize assigns a different username and passwords to the every alumnus. Admin sends to Alumnus username and passwords to their e-mail address. Alumnus use their user accounts and they connect to the system. In this way, Alumnus can see the announcements; do searching, sending e-mail to their old friends and their department, adding photo album also following news about department.

### Purpose, scope, and objectives

The purpose of “CTIS Alumni” is to create connection between CTIS department and graduated students from CTIS. On the other hand the software system provides connection of graduated students each other.

The objectives of the project:

- To hold the data that has access to information of the CTIS Alumni’s.

- To provide connection between Alumni and Alumnus.

- To provide connection between CTIS department and Alumnus.

- To make announcements to the Alumnus and Instructors

- To make convenience between Alumnus to find each other’s information which are not hidden.

The scope of the project:

The purpose of this product which is Web-based Tracking System for CTIS Alumni is to connect Alumnus and CTIS Department with creating an account for every Alumni and Instructor. The product contains two different interfaces, one of them is for Alumni and the other one is for Admin. Admin privileges’ cover Alumnus privileges.

- Admin shall make an announcement

- Admin shall create an alumni account.

- Admin shall manage and delete alumni’s account.

- Admin shall add, delete and edit announcements.

- Admin shall modify site status.

- Admin shall control site’s language filter.

- Users shall create and share their photo albums.

- Users shall send e-mail to one or more members.

- Users shall make comprehensive searching.

- Users shall update their information.

- Users shall view alumni according the year.

The out of scope of the project:

- Alumni do not have permission to create a new account.

- Alumni do not have permission to add, delete or edit a new announcement.

- Alumni do not have permission to change site status.

- Alumni do not have permission to add a bad word to language filter.

- Users can not enter any band word in anywhere of the site

### Assumptions and Constraints

#### Assumptions

The assumptions of the project are;

- The numbers of the project members are four (4) people and each person will work thirty five (35) hours per week.

- The project will be supplied by the team members or their own software.

- The CTIS department will supply appropriate server which is related to our project.

- The CTIS department will provide an account which is used by the existing program.

- The customer will provide adequate access to requirements and the information needed for the project.

#### Constraints

The constraints of the project are;

- Customer and project members determine using C# language.

- This project requires Microsoft Windows 2000 or higher operating system with .NET Framework 2.0.

- Modeling by the project to use Microsoft Visio.

- Creating GANTT chart, uses Microsoft Office Project.

- For database designing, uses Sybase PowerDesigner.

- As a database management system will be used MySQL.

- The documentation of the project will be implemented by IEEE standards [1,2].

- The requirements can only change by the customer, whose name is Aysin SOLAK ÖRKÇÜOĞLU.

### Project Deliverables

- An executable application including setup.

- User’s Manual

Deliverables may change during the progress of the project.

The table below shows the Deliverables listed by the Senior Project Manager Beyhan Akporay.

| Product: | Delivery Information: |
| --- | --- |
| Initial Plan: | The initial plan of the project is going be prepared until October 17th, 2008 and submitted to the project manager Beyhan Akporay. It has delivered both as a hard copy and a soft copy via e-mail. |
| Software Requirement Specification(SRS): | The Software Requirements Specification (SRS) document will be prepared on November 3rd , 2008 and submitted to the senior project manager Beyhan Akporay. It has delivered both as a hard copy and a soft copy via e-mail. |
| Software Project Management Plan(SPMP): | The Software Project Management Plan (SPMP), which is controlling documents and planning and organizing the software project, is going to be prepared on November 28th , 2008 and submitted to Beyhan Akporay. It will be delivered both as a hard copy and a soft copy via e-mail. |
| Software Design Document(SDD): | The Software Design Document (SDD) is a description of software which will be prepared on December 23rd, 2008 to Beyhan Akporay. It will be delivered both as a hard copy and a soft copy via e-mail. |
| Prototype Implementation & Demo | Web-Based Tracking System’s documentation will be presented to customer on January 2009. |
| Delivery of the Product | Web-Based Tracking System will be delivered to customer on May 2009. |

Table 1 Project Deliverables

### Schedule and Budget Summary

There is no Budget summary in this part of the document.

## Evolution of the SPMP

This task is the first version of the initial plan. For specifying files there is a file name where it may update files. The following is the file naming format.

| Document Name | File Name |
| --- | --- |
| Team19_InitialPlan | Team19_InitialPlan_vX.YYen.doc |

Table 2 : SPMP Evolution

The explanation of this format shows below;

- X is the version number of the project which indicates the scheduled revisions of the project.

- Y is the revision number of the project which indicates the unscheduled updates or changes.

- The suffix “en” means the shortened form of English that document is going to be written by.

In addition, if the system needs any update, we will serve a new version of this product to customer.

# References

## Book, Documents

[1]   IEEE STD 1058-1998, IEEE Standard for Software Project Management Plans

[2]   http://139.179.33.221/alumni/index.php

[3]   IEEE Std. 1058-1998, IEEE Standard for Software Project Management Plans

[4] IEEE Std. 830-1998, IEEE Recommended Practice for Software Requirements Specifications

[5]	 IEEE Std. 1063-1998,IEEE Standard for Software User Documentation

[6]	 IEEE Std. 1042-1987 IEEE for Software Configuration Management

## Web References

[1]   http://www.selectminds.com/jsp/Front/Main.jsp?cmd=resource&page=home.shtml

[2]   http://sourceforge.net/project/showfiles.php?group_id=54254

# Definitions and Abbreviations

## Definitions

Acquirer: Specifies requirements for the WTS and accepts delivery of a new or modified software product. In this project acquirer is CTIS instructor Ayşin ÖRKÇÜOĞLU.

Project Team: That is a team which is developing the WTS project. It refers to, Bora Korkmaz, Bengü Karakoç, Burçak Aydın, Gizem Selek

.Web-based Tracking System (WTS): Define a software system that is prepared by using web-based tools.

CTIS Alumni: A person who has received a degree from the department of CTIS.

Admin: Refers to person who controls, maintains the system and has authorization to manage members.

Alumni: A person who graduate from CTIS department.

Software Project: Technical and managerial work activities that required satisfying the terms and conditions of a project agreement.

Project Deliverable: A work product to be delivered to the acquirer, by the delivery dates, delivery location and the satisfaction for the project agreement.

Work Product: An item which tangible which is produced during the process of developing or modifying software.

.NET Framework: The Microsoft .NET Framework is a software technical methods which is practicable with few Microsoft Windows operating systems.

## Abbreviations

| WBTSCA: | Web-Based Tracking System for CTIS Alumni |
| --- | --- |
| WTS: | Web-Based Tracking System |
| CTIS: | Computer Technology and Information System |
| DBMS: | Database Management Systems |
| SRS: | Software Requirements Specification |
| SW: | Software |
| HW: | Hardware |
| IS: | Information Systems |
| SDD: | Software Design Document |
| SPMP: | Software Project Management Plan |
| C# .NET: | A Computer Language |
| IEEE: | Institute of Electric & Electrical Engineering |
| WBS: | Work Breakdown Structure |
| GUI: | Graphical User Interface |
| SPMP: | Software Project Management Plan |
| DB: | Database |
| SA: | Systems Administrator |
| WTS: | Web-Based Tracking System |
| Ver. #: | Version Number |
| DRT: | Duration |
| THRS: | Total Hours of Work |
| MS Project: | Microsoft Office Project 2003 |
| MS Word: | Microsoft Office Word 2003 |

Table 3 Abbrevations

# Project Organization

A project organization will only exist from the projects start until its end and it defines project members’ roles and their responsibilities while the project continues. All members in the project team does their work should be comprehensible, and effective for the good product.

## External Interfaces

- Project Group: Project Team consists of 4 members:

BoraKORKMAZ, Bengü KARAKOÇ, Burçak AYDIN, Gizem SELEK,

- Consultant: 	  Ayşın Solak ÖRKÇÜOĞLU

- User: 		  CTIS Alumnus and CTIS Instructors

- Acquirer: 	  Bilkent University – Computer Technology and Information Systems.

The project members communicate each other via e-mail and cellular phone on the other hand they get together 3 days of a week.

This schema shows the external structure of the WTS project group

Figure 1 : External Interfaces

## Internal Interfaces

Team members of the project always communicate each other about project situation in every changes and every new adding.

This schema shows the internal structure of the WTS project group

Figure 2 : Internal Structure

## Roles and Responsibilities

Listed below are the roles and responsibilities of whose is working in the senior project.

| Team Member | e-mail | Role |
| --- | --- | --- |
| Elif Bengü Karakoç | ekarakoc@ug.bilkent.edu.tr | - Project Manager Team - Documentation Team - Quality Team - Testing Team - Requirements Analysis Team |
| Bora Korkmaz | bkorkmaz@ug.bilkent.edu.tr | - Coding Team - Database Management Team - Design Team - Configuration Team - Documentation Team |
| Gizem Selek | gselek@ug.bilkent.edu.tr | - Coding Team - Database Team - Configuration Team - Quality Team - Documentation Team |
| Meliha Burçak Aydın | mbaydin@ug.bilkent.edu.tr | - Requirements Team - Design Team - Documentation Team - Testing Team |

Table 4 : Roles

| Role | Description |
| --- | --- |
| Project Manager | Making a schedule and also responsible to plan the division of the work to complete the segments of the project. |
| Requirements Analysis Team | Deciding the requirements of the project while fix the boundaries in phase of the project. |
| Coding Team | Doing the coding according to the acquirer’s specifications and the project requirements. |
| Documentation Team | Preparing all of the documentation about project. |
| Database Management Team | Making the implementation and the manipulation of the database system of the project. |
| Design Team | Responsible for the design of the project. |
| User Interface Team | Making the GUI of the project more user-friendly to meet the specifications of the acquirer. |
| Test Team | Testing the project in order to measure the quality of developed software. |
| Configuration Team | Controlling different versions of the work products. |
| Quality Assurance Team | Reporting the quality of the system based on the reports coming from requirements analysis team and testing team. |

Table 5 : Team Roles and Responsibilities

# Managerial process plans

## Project Start-up Plan

### Estimation Plan

In this part of the project, estimating the cost of the project will be specified. Methods, tools, techniques, cost and schedule will be used to estimate cost of the project. Function method is used for estimating project size. In order help to identify function points user requirements which are identified during meetings with acquirer. The table below is the complexity of calculation the function point.

| Description | Type (a) | Number of DETs | Number of FTRs/RETs | Complexity (b) |
| --- | --- | --- | --- | --- |
| User Data | ILF | 28 | 2 | High |
| Administrator Data | ILF | 28 | 2 | High |
| News Data | ILF | 2 | 2 | Low |
| Status Data | ILF | 1 | 1 | Low |
| Language Filter Data | ILF | 1 | 1 | Low |
| Error Log | EIF | 4 | 1 | Low |
| Login Request | EI | 2 | 1 | Low |
| Update Info Request | EI | 28 | 2 | High |
| View Alumni Year Request | EI | 1 | 1 | Low |
| Find Member Request | EI | 2 | 1 | Low |
| View News Request | EI | 1 | 1 | Low |
| Edit Alumni Info Request | EI | 2 | 1 | Low |
| Add Alumni Request | EI | 5 | 1 | Low |
| Send Mass Mail Request | EI | 3 | 1 | Low |
| Send Individual Mail Request | EI | 3 | 2 | Low |
| Change Status Request | EI | 1 | 1 | Low |
| Add News Request | EI | 4 | 1 | Low |
| Edit News Request | EI | 4 | 1 | Low |
| Change Filter Request | EI | 1 | 1 | Low |
| Display User(s) | EQ | 3 | 1 | Low |
| Display All News | EQ | 2 | 1 | Low |
| Display Year | EQ | 2 | 1 | Low |
| Edit User Display | EQ | 5 | 1 | Low |
| Display User Info | EO | 5 | 1 | Low |
| Display Individual News | EO | 3 | 2 | Low |

Table 6 : ILF, EIF, EI, EO and EQ

|  | Simple | Average | High | Total |
| --- | --- | --- | --- | --- |
| (EI) External input | 12 x 3 | x 4 | 1 x 6 | 42 |
| (EO) External output | 2 x 4 | x 5 | x 7 | 8 |
| (EQ) External enquiry | 4 x 3 | x 4 | x 6 | 12 |
| (ILF) Internal logical file | 3 x 7 | x 10 | 2 x 15 | 51 |
| (EIF) External interface file | 1 x 5 | x 7 | x10 | 5 |
| Total FP (UFP) = 118 |  |  |  |  |

Table 7 : Unadjusted Function Point

To find the size of the system in terms of LOC (Line of Code) we multiply UFP with 30 because the project team will be developing the project with C# language which is equal to the size of Java code.

30 * 118 = 3540

Almost all of the software project engineers use Constructive Cost Model (COCOMO) for making the cost estimation of the software product. It can be applied to almost all kind and size of software projects.

For effort estimation;

Effort = a * Size b

We are developing the project with the COCOMO organic mode, for that reason “a” is equal to 2,4 and “b” is equal to 1,05.

Effort = 2,4 * 3,51.05  8,9 person months

For schedule estimation;

TDEV = c * Ed

TDEV = 2,5 * 8,90,38   5,7 Months

For Average staffing estimation;

8,9 / 5,7 = 2 People

For Product Design Effort;

PDE = 8,9 %16 = 1,42 Person Months

For Product Design Schedule;

PDS = 1,42 %19 = 0,3 Month

For Total Cost;

Total Hours = Day * Hour * TDEV

TH = 20 * 3 * 5,7 = 342 hours

Total Cost = $10 * Total Hour * People

TC = $10 * 342 * 4 = $13680

### Staffing Plan

In our project we have 4(four) members whom are the senior students. The below table shows the roles and skills of the project by project phase.

| ID | Project Phase | Role | Skills Required | Number of Staff Required | Duration Required |
| --- | --- | --- | --- | --- | --- |
| 1 | WTS for CTIS |  |  | 4 | 169 days |
| 2 | Identify problem | SW Requirement Analysis Team | SW Requirements Documentation expert | 4 | 6 days |
| 3 | Meeting with acquirer | SW Quality Team & SW Requirement Analysis Team | Quality control & Quality assurance expert | 4 | 1 day |
| 4 | Initial Plan |  |  | 4 | 6.4 days |
| 5 | Preparation of Initial Plan | SW documentation team | SW Requirements Documentation expert | 4 | 6 day |
| 6 | Review of Initial Plan | SW Quality Team | Quality control & Quality assurance expert | 4 | 3 hours |
| 7 | Submit Initial Plan version 1.0 | SW documentation team | SW Requirements Documentation expert | 4 | 1 hour |
| 8 | Software Requirements Specifications |  |  | 4 |  |
| 9 | Review of Existing CTIS ALUMNI System | SW Requirement Analysis Team | SW Requirements Documentation expert | 4 | 2 days |
| 10 | Identify user requirements | SW Requirement Analysis Team | SW Requirements Documentation expert | 4 | 29.5 hours |
| 11 | Identify Non-Functional Requirements | SW Requirement Analysis Team | SW Requirements Documentation expert | 4 | 15 hours |
| 12 | Preparation of SRS | SW documentation team | SW Requirements Documentation expert | 4 | 8 days |
| 13 | Review of SRS | SW Quality Team | Quality control & Quality assurance expert | 4 | 3 hours |
| 14 | Submit SRS | SW documentation team | SW Requirements Documentation expert | 4 | 1 hour |
| 15 | Software Project Management Plan |  |  | 4 | 76.6 hours |
| 16 | Review of Initial plan | SW documentation team | SW Requirements Documentation expert | 4 | 7.7 hours |
| 17 | Work activities definitions | SW documentationteam | SW Requirements Documentation expert | 4 | 6.9 hours |
| 18 | Schedule, budget and resource allocation determination | SW documentation team | SW Requirements Documentation expert | 4 | 7 hours |
| 19 | Determine metrics | SW documentation team | SW Requirements Documentation expert | 4 | 5 hours |
| 20 | Determine risk management methodologies | Swdocumentation team | SW Requirements Documentation expert | 4 | 6 hours |
| 21 | PreparationofSPMP | SW documentation team | SW Requirements Documentation expert | 4 | 40 hours |
| 22 | Review of SPMP | SW Quality Team | Quality control & Quality assurance expert | 4 | 3 hours |
| 23 | Submit SPMP | SW documentation team | SW Requirements Documentation expert | 4 | 1 hours |
| 24 | Software Design Documentation |  |  | 4 | 127 hours |
| 25 | Functional Design |  |  | 4 | 45 hours |
| 26 | Administrator Functions | SW Design Team | SW Design expert | 4 | 29 hours |
| 27 | User Functions | SW Design Team | SW Design expert | 4 | 16 hours |
| 28 | DB Design |  |  | 4 | 10 hours |
| 29 | Preparation of SDD | SW documentation team | SW Requirements Documentation expert | 4 | 35 hours |
| 30 | Review of SDD | SW Quality Team | Quality control & Quality assurance expert | 4 | 36 hours |
| 31 | Submit SDD | SW documentation team | SW Requirements Documentation expert | 4 | 1 hour |
| 32 | Coding and Testing |  |  | 4 | 98 hours |
| 33 | DB Coding | SW Database Management Team | SW Database Management expert | 4 | 20 hours |
| 34 | Functional coding |  |  | 4 | 62 hours |
| 35 | Training of C# Net | SW coding Team | SW coding expert | 4 | 16 hours |
| 36 | Deciding the coding structure | SW coding Team | SW coding expert | 4 | 11 hours |
| 37 | Code and Test Administrator functions | SW Coding& Testing Team | SW Coding& Testing expert | 4 | 18 hours |
| 38 | Code and Test User functions | SW Coding& Testing Team | SW Coding& Testing expert | 4 | 17 hours |
| 39 | Meeting with acquirer about project code | SW Quality Team & SW Requirement Analysis Team | Quality control & Quality assurance expert | 4 | 1 hour |
| 40 | Submit project coding ver. 1.0 | SW documentationteam | SW Requirements Documentationexpert | 4 | 1 hour |
| 41 | Software Integration and Testing | SW Testing Team | SW Testing expert | 4 | 6 hour |
| 42 | Installation |  |  | 4 | 80 hours |
| 43 | Installation of system SW | SW User Interface Team | SW User Interface expert | 4 | 6 hour |
| 44 | Prepare System Users | SW User Interface Team | SW User Interface expert | 4 | 74 hour |
| 45 | Prepare User manual | SW User Interface Team | SW User Interface expert | 4 | 60 hours |
| 46 | Documentation of User Manual | SW Documentation Team | SW Documentation expert | 4 | 12 hours |
| 47 | Meeting with acquirer about user Manual | SW Quality Team & SW Requirement Analysis Team | Quality control & Quality assurance expert | 4 | 1 hour |
| 48 | SubmitUserManual ver 1.0 | SW documentationteam | SW Requirements Documentationexpert | 4 | 1 hour |
| 49 | Product Delivery |  |  | 4 | 37 hours |
| 50 | Organizing Project deliverable | SW configuration management Team | SW configuration management expert | 4 | 6 hours |
| 51 | ConfigurationManagement | SW configuration management Team | SW configuration management expert | 4 | 30 hours |
| 52 | Demonstration of the Project | All of group team | All of group team | 4 | 1 hour |

Table 8 : Staff Planning

### Resource acquisition plan

N/A

### Project staff training plan

For personal development, all the group members will need to have a training program. Group members will search their training methodologies by themselves from books and internet. These trainings will be about programming language and development tools and platforms. Following table will show the training schedule of our team.

| ID | Training | Resource | Start | End | Duration |
| --- | --- | --- | --- | --- | --- |
| 1 | Standards | Burçak[65] | 07.10.2008 | 10.11.2008 | 33 days |
| 2 | Sybase | Bora[67] | 15.10.2008 | 12.11.2008 | 27 days |
| 3 | C# | Gizem[70] | 15.10.2008 | 12.11.2008 | 27 days |
| 4 | Testing procedures | Bengi[74] | 07.10.2008 | 12.11.2008 | 65 days |

Table 9 :  Staff Training Plan Table

## Work plan

### Work activities

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.1 |
| Activity/Task Name | IDENTIFY_PROBLEM |
| Activity/task Description | Specify the main purpose of the WTS for Ctis Alumni. |
| Estimated Duration | 6 days |
| Resources Needed |  |
| - Personnel | Bengi,Burçak |
| - Skills | Above the two of the group member will be familiar with the requirements analysis and communication is an important factor for solving the problem. |
| - Software | Existing “CTIS ALUMNI” web site. |
| - Hardware | Notebook |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Understanding the problem and the main purpose of the project and find solutions. |

Table 10 : Work Package Specification (Activity 1.1)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.1.1 |
| Activity/Task Name | MEETING_WITH_ACQUIRER |
| Activity/task Description | Specify the activities of the WTS for Ctis Alumni with acquirer. |
| Estimated Duration | 1 day |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | All the group members will have better communication skills and also all of them will master of the project. |
| - Software | None |
| - Hardware | Notebook is the most important thing to note meeting details. |
| - Travel | None |
| Product(s) to be generated when completed: | Limitation of the activities in the project. |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria:ş | Acquirer acceptance |

Table 11 : Work Package Specification (Activity 1.2)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.2.1 |
| Activity/Task Name | PREPARATION_INITIAL_PLAN |
| Activity/task Description | Specify the IEEE standards and deciding the cases of initial plan of the project. |
| Estimated Duration | 6 days |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | All the group members will have knowledge about IEEE standards ,project documentation ability and brainstorming. |
| - Software | MS Project tool for GANTT chart, MS Word tool for writing the document. |
| - Hardware | IEEE document for the template of the initial plan |
| - Travel | None |
| Product(s) to be generated when completed: | Initial plan of the project. |
| Predecessor Tasks: | None |
| Successor Tasks: | 2.3 (Submit initial plan ver 1.0) |
| Risks: | -Misunderstanding the IEEE standards -Not finish on time(Due date of the initial plan) |
| Completion Criteria: | Documentation of the initial plan |

Table 12 : Work Package Specification (Activity 1.2.1)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.2.2 |
| Activity/Task Name | REVIEW_INITIAL_PLAN |
| Activity/task Description | The Initial plan is updated according to the issues of the Initial Plan Review report. |
| Estimated Duration | 3 hours |
| Resources Needed |  |
| - Personnel | Bengi,Gizem |
| - Skills | Two of the group member will have knowledge about Quality for controlling the initial plan. |
| - Software | MS Word. |
| - Hardware | Feedback of our initial Plan |
| - Travel | None. |
| Product(s) to be generated when completed: | Initial Plan(V2.0) |
| Predecessor Tasks: | 1.2.1-İnitial Plan ver 1.0 |
| Successor Tasks: | None |
| Risks: | Misunderstanding the feedback |
| Completion Criteria: | The Initial plan is updated according to the feedback. |

Table 13 : Work Package Specification (Activity 1.2.2)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.2.3 |
| Activity/Task Name | SUBMIT_INITIAL_PLAN |
| Activity/task Description | Submit of the initial plan ver 1.0 according to death line of due date. |
| Estimated Duration | 1 hour |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | Internet |
| - Hardware | Hard copy of the initial plan. |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.2.1-preparation of the initial plan |
| Successor Tasks: | None |
| Risks: | Failure sending e-mail to Beyhan Akporay. |
| Completion Criteria: | Submission of the initial plan |

Table 14 : Work Package Specification (Activity 1.2.3)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.3.1 |
| Activity/Task Name | REVIEW_EXISTING_SYSTEM |
| Activity/task Description | Specify the standards and regulations of the existing system and determine necessary thinks to add with acquirer. |
| Estimated Duration | 2 days |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | Know the existing user name and password in the existing “CTIS Alumni” system. |
| - Software | Internet |
| - Hardware | Notebook |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | Unknown username and password will be used. |
| Completion Criteria: | Examination of the standards and regulations with acquirer for necessary in the system. |

Table 15 : Package Specification (Activity 1.3.1)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.3.2 |
| Activity/Task Name | IDENTIFY_USER_REQUIREMENTS |
| Activity/task Description | During meeting with acquirer, user requirements are identified. |
| Estimated Duration | 29.5 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak |
| - Skills | Brainstorming |
| - Software | None |
| - Hardware | Notebook |
| - Travel | None |
| Product(s) to be generated when completed: | Use case of the system |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | Misunderstanding the user requirements |
| Completion Criteria: | User requirements are identified. |

Table 16 : Work Package Specification (Activity 1.3.2)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.3.3 |
| Activity/Task Name | IDENTIFY_NONFUNCTIONAL_REQUIREMENTS |
| Activity/task Description | Identify performance requirements. |
| Estimated Duration | 15 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak |
| - Skills | Two of the group members will know what the nonfunctional requirements are. |
| - Software | MS word |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | Performance requirements |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | Misunderstanding the nonfunctional requirements |
| Completion Criteria: | Performance requirements are identified. |

Table 17 : Work Package Specification (Activity 1.3.3)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.3.4 |
| Activity/Task Name | PREPARATION_SRS |
| Activity/task Description | User requirements, performance requirements will be used and also initial plan ver. 2.0 will be used. |
| Estimated Duration | 8 days |
| Resources Needed |  |
| - Personnel | Bengi, Burçak, Gizem, Bora |
| - Skills | None |
| - Software | MS Word |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | Documentation of SRS |
| Predecessor Tasks: | 1.2.2,1.3.2,1.3.3-initial plan ver.2.0,user requirements and performance requirements |
| Successor Tasks: | 1.3.6-submit of SRS |
| Risks: | Requirement analyzing |
| Completion Criteria: | SRS document is prepared according to IEEE Std-1058. |

Table 18 : Work Package Specification (Activity 1.3.4)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.3.5 |
| Activity/Task Name | REVIEW_SRS |
| Activity/task Description | SRS is updated according to the issues of the SRS Review report. |
| Estimated Duration | 3 hours |
| Resources Needed |  |
| - Personnel | Bengi,Gizem |
| - Skills | Two of the group members will know the quality for controlling the SRS by using the feedback. |
| - Software | MS Word |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | SRS ver.2.0 |
| Predecessor Tasks: | 1.3.4-preparation of SRS |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | SQT reviews the SRS by using given feedback. |

Table 19 : Work Package Specification (Activity 1.3.5)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.3.6 |
| Activity/Task Name | SUBMIT_SRS |
| Activity/task Description | Submit of the SRS according to death line of the due date. |
| Estimated Duration | 1 hours |
| Resources Needed |  |
| - Personnel | Bora |
| - Skills | None |
| - Software | Internet |
| - Hardware | 1 hard copy |
| - Travel | None |
| Product(s) to be generated when completed: | 1 hard copy and 1 soft copy of the SRS. |
| Predecessor Tasks: | 1.3.4-preparation of SRS |
| Successor Tasks: | None |
| Risks: | Failure sending e-mail to Beyhan Akporay |
| Completion Criteria: | Submission of SRS |

Table 20 : Work Package Specification (Activity 1.3.6)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.4.1 |
| Activity/Task Name | REVIEW_INITIAL_PLAN |
| Activity/task Description | Before the preparation of SPMP,initial plan will be reviewed. |
| Estimated Duration | 7.7 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | None |
| - Hardware | Documentation of Initial Plan |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.2.2-review of initial plan |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | A preparation of SPMP |

Table 21 : Work Package Specification (Activity 1.4.1)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.4.2 |
| Activity/Task Name | DEFINE_WORK_ACTIVITIES |
| Activity/task Description | The major work activities are defined. |
| Estimated Duration | 6.9 hours |
| Resources Needed |  |
| - Personnel | Gizem,Burçak |
| - Skills | Two of the group member will know the WBS of the system. |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | A table with WBS activities. |
| Predecessor Tasks: | 1.2.1-initial plan(WBS) |
| Successor Tasks: | None |
| Risks: | Misunderstanding the WBS |
| Completion Criteria: | Major activities are defined and decomposed into work packages. |

Table 22 : Work Package Specification (Activity 1.4.2)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.4.3 |
| Activity/Task Name | SCHEDULE_BUDGET_RESOURCE_ALLOCATION |
| Activity/task Description | The schedule, budget and resource allocation tables will be prepared according to WBS. |
| Estimated Duration | 7 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | MS project |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | Schedule,budget,resource tables |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Schedule, budget, resource allocation tables |

Table 23 : Work Package Specification (Activity 1.4.3)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.4.4 |
| Activity/Task Name | DETERMINE_METRICS |
| Activity/task Description | The metrics to be used for project will be determined. |
| Estimated Duration | 5 hours |
| Resources Needed |  |
| - Personnel | Bora |
| - Skills | The member of this group will know the software metrics. |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | Metric Table |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Metrics to be used for the project. |

Table 24 : Work Package Specification (Activity 1.4.4)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.4.5 |
| Activity/Task Name | DETERMINE_RISK_MANAGEMENT |
| Activity/task Description | The risks will be identified and evaluated. |
| Estimated Duration | 6 hours |
| Resources Needed |  |
| - Personnel | Gizem,Bora |
| - Skills | Two of the group member will know the risk management methodologies. |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | Risk Plan |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Identified risks, risk planning processes |

Table 25 : Work Package Specification (Activity 1.4.5)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.4.6 |
| Activity/Task Name | PREPERATION_SPMP |
| Activity/task Description | After Work activities,metrics,risks,schedule,budget,resources and technical processes are identified SPMP will be prepared by using these activities. |
| Estimated Duration | 40 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | MS Word |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | Documentation of SPMP |
| Predecessor Tasks: | 1.4.1,1.4.2,1.4.3,1.4.4.1.4.5 |
| Successor Tasks: | 1.4.8-submit SPMP |
| Risks: | None |
| Completion Criteria: | The SPMP document is prepared according to IEEE std-1058. |

Table 26 : Work Package Specification (Activity 1.4.6)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.4.7 |
| Activity/Task Name | REVİEW_SPMP |
| Activity/task Description | SQT reviews the SPMP. |
| Estimated Duration | 3 hours |
| Resources Needed |  |
| - Personnel | Bengi,Gizem |
| - Skills | Two of the group member will know the quality of a software. |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.4.6 |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | None |

Table 27 : Work Package Specification (Activity 1.4.7)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.4..8 |
| Activity/Task Name | SUBMIT_SPMP |
| Activity/task Description | SPMP will be submitted according to due date. |
| Estimated Duration | 1 hours |
| Resources Needed |  |
| - Personnel | Bora |
| - Skills | None |
| - Software | Internet |
| - Hardware | 1(one) hard copy of the SPMP |
| - Travel | None |
| Product(s) to be generated when completed: | Documentation of the SPMP |
| Predecessor Tasks: | 1.4.6-preparation of SPMP |
| Successor Tasks: | None |
| Risks: | Failure sending e-mail to Beyhan Akporay |
| Completion Criteria: | Submission of SPMP |

Table 28 : Work Package Specification (Activity 1.4.7)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.5.1 |
| Activity/Task Name | FUNCTIONAL_DESIGN |
| Activity/task Description | Administrator and user functions of the system. |
| Estimated Duration | 45 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak |
| - Skills | None |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | none |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Decomposed the functional design. |

Table 29 : Work Package Specification (Activity 1.5)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.5.1.1 |
| Activity/Task Name | ADMINISTRATOR_FUNCTIONS |
| Activity/task Description | The design of the administrator functions of the system will be identified. |
| Estimated Duration | 29 hours |
| Resources Needed |  |
| - Personnel | Bora,Burçak |
| - Skills | Two of the group member will know the administrator activities and according to this design the system. |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | Design of the administrator functions of the system. |
| Predecessor Tasks: | 1.3.4 |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | SRS document is reviewed and depending on the requirements defined, design of admistrator functions are made. |

Table 30 : Work Package Specification (Activity 1.5.1.1)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.5.1.2 |
| Activity/Task Name | USER_FUNCTIONS |
| Activity/task Description | Alluser functions design |
| Estimated Duration | 16 hours |
| Resources Needed |  |
| - Personnel | Bora,Burçak |
| - Skills | Two of the group member will know the user functions of the system. |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.3.4 |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | SRS document is reviewed and depending on the requirements defined, design of user functions are made. |

Table 31 : Work Package Specification (Activity 1.5.1.2)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.5.2 |
| Activity/Task Name | DB_DESIGN |
| Activity/task Description | All user functions and administrator functions will be designed. |
| Estimated Duration | 10 hours |
| Resources Needed | pğ |
| - Personnel | Gizem,Bora |
| - Skills | Two of the group member will know the database designing. |
| - Software | Sybase |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.5.1.1,1.5.1.2 |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Depending on the requirements defined in SRS and by reviewing alluser functions and administrator functions a database desing is prepared. |

Table 32 : Work Package Specification (Activity 1.5.2)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.5.3 |
| Activity/Task Name | PREPERATION_SDD |
| Activity/task Description | User functions,administrator functions and database design will be used. |
| Estimated Duration | 35 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | None |
| - Hardware | MS Word |
| - Travel | None |
| Product(s) to be generated when completed: | Documentation of SDD |
| Predecessor Tasks: | 1.5.1.1,1.5.1.2,1.5.2 |
| Successor Tasks: | 1.5.5 |
| Risks: | None |
| Completion Criteria: | SDD prepared by using user functions,administrator functions and database design. |

Table 33 : Work Package Specification (Activity 1.5.3)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.5.4 |
| Activity/Task Name | REVIEW_SDD |
| Activity/task Description | SDD document is reviewed by SQT according to IEEE Std-1058 |
| Estimated Duration | 36 hours |
| Resources Needed |  |
| - Personnel | Bengi,Gizem |
| - Skills | Two of the group member will know the quality of software. |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | SDD Review Report |
| Predecessor Tasks: | 1.5.3 |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | SDD document is review by using given feedback. |

Table 34 : Work Package Specification (Activity 1.5.4)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.5.5 |
| Activity/Task Name | SUBMIT_SDD |
| Activity/task Description | Submission of SDD according to due date. |
| Estimated Duration | 1 hour |
| Resources Needed |  |
| - Personnel | Bora |
| - Skills | None |
| - Software | Internet |
| - Hardware | 1 hard copy of the SDD |
| - Travel | None |
| Product(s) to be generated when completed: | Documentation of SDD |
| Predecessor Tasks: | 1.5.3 |
| Successor Tasks: | None |
| Risks: | Failure sending e-mail to Beyhan Akporay |
| Completion Criteria: | Submission of SDD |

Table 35 : Work Package Specification (Activity 1.5.5)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.6.1 |
| Activity/Task Name | DB_CODING |
| Activity/task Description | The DB is created according to the DB design defined in SDD. |
| Estimated Duration | 20 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak |
| - Skills | Testing cases |
| - Software | Sybase |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.5.5 |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Created Database |

Table 36 : Work Package Specification (Activity 1.6.1)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.6.2 |
| Activity/Task Name | FUNCTIONAL_CODING |
| Activity/task Description | Specify Training of C# Net, Deciding the coding structure, Code and Test Administrator functions, Code and Test User functions. |
| Estimated Duration | 62 hours |
| Resources Needed |  |
| - Personnel | Gizem, Bora |
| - Skills | None |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Functional code of the system |

Table 37 : Work Package Specification (Activity 1.6.2)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.6.2.1 |
| Activity/Task Name | TRAINING_C#_NET |
| Activity/task Description | For personal development learning C# Net |
| Estimated Duration | 16 hours |
| Resources Needed |  |
| - Personnel | Gizem |
| - Skills | None |
| - Software | Internet |
| - Hardware | Books |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Learning about C# Net |

Table 38 : Work Package Specification (Activity 1.6.2.1)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.6.2.2 |
| Activity/Task Name | DECIDE_CODING_STRUCTURE |
| Activity/task Description | Determining the coding structure of the system. |
| Estimated Duration | 11 hours |
| Resources Needed |  |
| - Personnel | Gizem, Bora |
| - Skills | None |
| - Software | None |
| - Hardware | Notebook |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.6.2.3 |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Identify the coding structure |

Table 39 : Work Package Specification (Activity 1.6.2.2)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.6.2.3 |
| Activity/Task Name | CODE_TEST_ADMINISTRATOR_FUNCTIONS |
| Activity/task Description | Administrator functions are created according to the administartor function designes defined in SDD. |
| Estimated Duration | 18 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | All of the group members will know the .Net and testing procedures. |
| - Software | NET, Microsoft Visual Studio |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | Administrator functions, test results. |
| Predecessor Tasks: | 1.6.2.2 |
| Successor Tasks: | None |
| Risks: | Bug fixing |
| Completion Criteria: | Administrator functions will be created. |

Table 40 : Work Package Specification (Activity 1.6.2.3)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.6.2.4 |
| Activity/Task Name | CODE_TEST_USER_FUNCTIONS |
| Activity/task Description | User functions are created according to the alluser function designes defined in SDD. |
| Estimated Duration | 17 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | All of the group members will know the .Net and testing procedures. |
| - Software | .NET, Microsoft Visual Studio |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | User Functions and test results |
| Predecessor Tasks: | 1.6.2.2 |
| Successor Tasks: | None |
| Risks: | Bug fixing |
| Completion Criteria: | User functions will be created. |

Table 41 : Work Package Specification (Activity 1.6.2.4)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.6.3 |
| Activity/Task Name | MEETING_WITH_ACQUIRER |
| Activity/task Description | Meeting with acquirer about the issues of project coding and testing. |
| Estimated Duration | 1 hour |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | None |
| - Hardware | Laptop |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Acquirer acceptance |

Table 42 : Work Package Specification (Activity 1.6.3)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.6.4 |
| Activity/Task Name | SUBMIT_PROJECT_CODE |
| Activity/task Description | Submitting the project code according to due date. |
| Estimated Duration | 1 hour |
| Resources Needed |  |
| - Personnel | Bora |
| - Skills | None |
| - Software | Internet |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | Failure sending e-mail to Beyhan Akporay. |
| Completion Criteria: | Submission of project code |

Table 43 : Package Specification (Activity 1.6.4)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.6.5 |
| Activity/Task Name | SOFTWARE_INTEGRATION_TESTING |
| Activity/task Description | All the coded functions will be integrated |
| Estimated Duration | 6 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak |
| - Skills | Two of the group member will know the testing procedures. |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | Integrated software, test results. |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Integrated software is tested before installation. |

Table 44 : Work Package Specification (Activity 1.6.5)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.7.1 |
| Activity/Task Name | INSTALL_SYSTEM_SOFTWARE |
| Activity/task Description | After the integration of system testing, the system software is installed for all user functions. |
| Estimated Duration | 6 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.6.2.3,1.6.2.4 |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Software is installed. |

Table 45 : Work Package Specification (Activity 1.7.1)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.7.2.1 |
| Activity/Task Name | PREPARE_USER_MANUAL |
| Activity/task Description | Explains how to use this system |
| Estimated Duration | 60 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | A detailed user manual |

Table 46 : Work Package Specification (Activity 1.7.2.1)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.7.2.2 |
| Activity/Task Name | DOCUMENTATION_USER_MANUAL |
| Activity/task Description | Explains how to use this system |
| Estimated Duration | 12 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | MS Word |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | User manual documentation. |
| Predecessor Tasks: | 1.7.2.1 |
| Successor Tasks: | 1.7.2.4 |
| Risks: | None |
| Completion Criteria: | Adetailed user manual documentation. |

Table 47 : Work Package Specification (Activity 1.7.2.2)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.7.2.3 |
| Activity/Task Name | MEETING_WITH_ACQUIRER |
| Activity/task Description | Meeting with acquirer about the user manual. |
| Estimated Duration | 1 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | None |
| - Hardware | Notebook |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.7.2.2 |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Acquirer Acceptance |

Table 48 : Work Package Specification (Activity 1.7.2.3)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.7.2.4 |
| Activity/Task Name | SUBMIT_USER_MANUAL |
| Activity/task Description | Submission of user manual according to due date. |
| Estimated Duration | 1 hour |
| Resources Needed |  |
| - Personnel | Bora |
| - Skills | None |
| - Software | Internet |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.7.2.2 |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Submission of user manual |

Table 49 : Work Package Specification (Activity 1.7.2.4)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.8.1 |
| Activity/Task Name | ORGANIZE_PROJECT_DELIVERABLE |
| Activity/task Description | Organizing the project deliverable, prepare product presentation |
| Estimated Duration | 6 hours |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | None |
| - Software | None |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | None |
| Successor Tasks: | None |
| Risks: | None |
| Completion Criteria: | Prepare product presentation |

Table 50 : Work Package Specification (Activity 1.8.1)

| WORK PACKAGE SPECIFICATION |  |
| --- | --- |
| Activity/Task Number: | 1.8.3 |
| Activity/Task Name | DEMONSTRATION_PROJECT |
| Activity/task Description | Presentation of project |
| Estimated Duration | 1 hour |
| Resources Needed |  |
| - Personnel | Bengi,Burçak,Gizem,Bora |
| - Skills | Communication |
| - Software | Project Demo |
| - Hardware | None |
| - Travel | None |
| Product(s) to be generated when completed: | None |
| Predecessor Tasks: | 1.8.1 |
| Successor Tasks: | None |
| Risks: | Excited for communication |
| Completion Criteria: | Demo of the product delivery |

Table 51 : Package Specification (Activity 1.8.3)

### Schedule allocation

| ID | WBS# | Task Name | Start Date | Finish Date | Duration | Milestones |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | WTS for CTIS | 07.10.08 | 29.05.08 | 169 days |  |
| 2 | 1.1 | Identify problem | 07.10.08 | 14.10.08 | 6 days |  |
| 3 | 1.1.1 | Meeting with acquirer | 11.10.08 | 11.10.08 | 1 day |  |
| 4 | 1.2 | Initial Plan | 11.10.08 | 17.10.08 | 6.4 days | + |
| 5 | 1.2.1 | Preparation of Initial Plan | 11.10.08 | 17.10.08 | 6 day |  |
| 6 | 1.2.2 | Review of Initial Plan | 02.11.08 | 02.11.08 | 3 hours |  |
| 7 | 1.2.3 | Submit Initial Plan version 1.0 | 17.10.08 | 17.10.08 | 1 hour |  |
| 8 | 1.3 | Software Requirements Specifications | 19.10.08 | 03.11.08 |  | + |
| 9 | 1.3.1 | Review of Existing CTIS ALUMNI System | 19.10.08 | 21.10.08 | 2 days |  |
| 10 | 1.3.2 | Identify user requirements | 21.10.08 | 23.10.08 | 29.5 hours |  |
| 11 | 1.3.3 | Identify Non-Functional Requirements | 24.10.08 | 26.10.08 | 15 hours |  |
| 12 | 1.3.4 | Preparation of SRS | 26.10.08 | 03.11.08 | 8 days |  |
| 13 | 1.3.5 | Review of SRS | 28.11.08 | 28.11.08 | 3 hours |  |
| 14 | 1.3.6 | Submit SRS | 03.11.08 | 03.11.08 | 1 hour |  |
| 15 | 1.4 | Software Project Management Plan | 04.11.08 | 28.11.08 | 76.6 hours | + |
| 16 | 1.4.1 | Review of Initial plan | 04.11.08 | 04.11.08 | 7.7 hours |  |
| 17 | 1.4.2 | Work activities definitions | 05.11.08 | 05.11.08 | 6.9 hours |  |
| 18 | 1.4.3 | Schedule, budget and resource allocation determination |  |  | 7 hours |  |
| 19 | 1.4.4 | Determine metrics | 10.11.08 | 10.11.08 | 5 hours |  |
| 20 | 1.4.5 | Determine risk management methodologies | 12.11.08 | 12.11.08 | 6 hours |  |
| 21 | 1.4.6 | Preparation of SPMP | 14.11.08 | 14.11.08 | 40 hours |  |
| 22 | 1.4.7 | Review of SPMP | 02.01.09 | 04.01.09 | 3 hours |  |
| 23 | 1.4.8 | Submit SPMP | 28.11.08 | 28.11.08 | 1 hours |  |
| 24 | 1.5 | Software Design Documentation | 29.11.08 | 30.12.09 | 127 hours | + |
| 25 | 1.5.1 | Functional Design | 29.11.08 | 02.12.08 | 45 hours |  |
| 26 | 1.5.1.1 | Administrator Functions | 03.12.08 | 05.12.08 | 29 hours |  |
| 27 | 1.5.1.2 | User Functions | 07.12.08 | 07.12.08 | 16 hours |  |
| 28 | 1.5.2 | DB Design | 08.12.08 | 08.12.08 | 10 hours |  |
| 29 | 1.5.3 | Preparation of SDD | 10.12.08 | 12.12.08 | 35 hours |  |
| 30 | 1.5.4 | Review of SDD | 22.01.08 | 23.01.08 | 36 hours |  |
| 31 | 1.5.5 | Submit SDD | 30.12.08 | 30.12.08 | 1 hour |  |
| 32 | 1.6 | Coding and Testing | 09.02.09 | 14.02.09 | 98 hours | + |
| 33 | 1.6.1 | DB Coding | 15.02.09 | 16.02.09 | 20 hours |  |
| 34 | 1.6.2 | Functional coding |  |  | 62 hours |  |
| 35 | 1.6.2.1 | Training of C# Net | 25.02.09 | 26.02.09 | 16 hours |  |
| 36 | 1.6.2.2 | Deciding the coding structure | 28.02.09 | 28.02.09 | 11 hours |  |
| 37 | 1.6.2.3 | Code and Test Administrator functions | 30.02.09 | 30.02.09 | 18 hours |  |
| 38 | 1.6.2.4 | Code and Test User functions | 03.03.09 | 03.03.09 | 17 hours |  |
| 39 | 1.6.3 | Meeting with acquirer about project code | 04.03.09 | 04.03.09 | 1 hour |  |
| 40 | 1.6.4 | Submit project coding ver. 1.0 | 09.03.09 | 09.03.09 | 1 hour |  |
| 41 | 1.6.5 | Software Integration and Testing | 14.03.09 | 14.03.09 | 6 hour |  |
| 42 | 1.7 | Installation |  |  | 80 hours | + |
| 43 | 1.7.1 | Installationofsystem SW | 16.03.09 | 16.03.09 | 6 hour |  |
| 44 | 1.7.2 | Prepare System Users | 18.03.09 | 25.04.09 | 74 hour |  |
| 45 | 1.7.2.1 | Prepare User manual | 18.03.09 | 21.04.09 | 60 hours |  |
| 46 | 1.7.2.2 | DocumentationofUser Manual | 22.04.09 | 22.04.09 | 12 hours |  |
| 47 | 1.7.2.3 | Meeting with acquirer about user Manual | 23.04.09 | 23.04.09 | 1 hour |  |
| 48 | 1.7.2.4 | Submit User Manual ver. 1.0 | 25.04.09 | 25.04.09 | 1 hour |  |
| 49 | 1.8 | Product Delivery | 27.04.09 | 29.05.09 | 37 hours | + |
| 50 | 1.8.1 | Organizing Project deliverable | 27.04.09 | 27.04.09 | 6 hours |  |
| 51 | 1.8.2 | Configuration Management | 05.05.09 | 28.05.09 | 30 hours |  |
| 52 | 1.8.3 | Demonstration of the Project | 29.05.09 | 29.05.09 | 1 hour |  |

Table 52 : Schedule of Work Activities and Milestones

### Resource allocation

Mostly the project group’s Resource Allocation Method is the Random Access Method. The main advantage is; everyone in the group has approximately the same skill with one and another. All of the group members might want to access a specific resource, so that the method for the group is Random Access Method.

| Software Project Phases | Deliverables | Resources | Tools |
| --- | --- | --- | --- |
| Requirements Analysis and Definition | (1) Initial Plan | Bora (25%) Bengi (25%) Burçak (25%) Gizem (25%) | Microsoft Office Word 2003 Microsoft Office Project Manager 2003 |
|  | (2) Software Requirements Specification | Bora (20%) Bengi (30%) Burçak (30%) Gizem (20%) | Microsoft Office Word 2003 Microsoft Office Project Manager 2003 Microsoft Office Visio 2003 MockUp Screens v3.17 |
| Estimation | Software Project Management Plan | Bora (25%) Bengi (25%) Burçak (25%) Gizem (25%) | Microsoft Office Word 2003 Microsoft Office Project Manager 2003 |
| Functional Specification and UI Prototype | - | Bora (30%) Bengi (20%) Burçak (30%) Gizem (20%) | Microsoft Office Word 2003 Mockup Screens v3.17 Microsoft Visual Studio 2008 |
| Software Architecture and Test Plan | Software Design Document | Bora (20%) Bengi (30%) Burçak (20%) Gizem (30%) | Microsoft Office Word 2003 Microsoft Office Visio 2003 |
| Implementation (Coding) and Testing | - | Bora (30%) Bengi (20%) Burçak (20%) Gizem (30%) | Microsoft Visual Studio 2008 Microsoft Office Word 2003 SyBase |
| Delivery and Installation | (1) Source Code (2) Software Product | Bora (25%) Bengi (25%) Burçak (25%) Gizem (25%) | - |
| Operation and Maintenance | - | Bora (25%) Bengi (25%) Burçak (25%) Gizem (25%) | Microsoft Visual Studio 2008 |

Table 53 : Resource Allocation

### Budget allocation

Refer to the section 5.1.1.

## Control plan

The aim of a process control plan is to control the product characteristics and the associated process variables to ensure capability and stability of the product over time. Control mechanisms will be done with accordance of IEEE standards.

### Requirements control plan

After determining requirements of the project by the customer, the group members, which related with the analyzing requirements, will construe and write these established requirements according to IEEE standards. After finishing requirements control by the team members, initial version of requirements documents will be forwarded to the customer. In every customer meetings should include reviewing all requirements and new requirements of the project because of the providing project’s requirements durability and correctness. All modifications in the requirements of the project will be record by the one of team members and these changes in the requirements will be controlled by the all team members and then customer whose name is Ayşın Solak Örkçüoğlu. These controls will be made with IEEE Std. 1042-1987 IEEE and this standard will be guided for Software Configuration Management.

Requirement Control Plan is made to sure that everything required will actually be done well and in time.

### Schedule control plan

The purpose of the schedule control plan will be helpful to make customer aware of what to be done and when the project will be delivered to them, and schedule control is to take measures for schedule delay. This project will be done between 17th of October 2008 and May 2009 according to schedule control plan. If there will be any delay about project cases, this situation will be share with the customer and solutions will be found by the project members. First solution is delivery date of the project cases not change only increasing work hours of the project members. If this solution way is not beneficial for the delivery of the milestones, there will be changes not only milestones schedule but also delivery of the project date.

### Budget control plan

None.

### Quality control plan

Quality plan, helps to schedule all of the tasks that is sure that the project meets the needs of the customer. In our project, the purpose of the quality plan is defined the tasks and activities in WBS which are focusing on achieving acquirer’s quality expectations. In addition, all group members follow IEEE standards for all the documentation. All the group members in our project fallow this project phases to improve the quality.

- Understand the user requirements better

- Determine the important functions

- Find good solutions to user requirements

Know how to make this project high quality

### Reporting plan

The most important part of the reporting plan is meeting with the customer so documents shall be prepared according to these meetings. All the part of these documentations, which are known as project deliverables, for Web-based Tracking System for CTIS Alumni shall be conformed to IEEE standards. In addition, project deliverables and their due dates are shown in 4.1.1.3 Project deliverables (*) and these documents will be prepared desired format. Using MS Project and MS Word are used to report for schedule, budget, and resource allocation. On the other hand, all prepared documents shall be sent to the acquirer by using e-mail so current status of the project will be reported to the acquirer. If the Project Manager will be informed directly via synchronous communication such as face-to-face meetings, communication manager keeps records of communicated issues and try to ensure this issue which is resolved necessary development. In addition, Quality control manager shall create meeting for controlling current status of development stage. On the other hand, project manager will be interacting with Customer and Quality Control Manager in case of every issue on project and they will use asynchronous communications such as e-mail in unimportant issues. Therefore, project team members will get together because they will perform status and view progress of the project.

Suggestions and reviews will be made.

### Metrics Collection Plan

| Metric | - Unit | Frequency of Collection |
| --- | --- | --- |
| Estimated Project Size | LOC | During Initial Plan and SPMP |
| Real Total Size | LOC | Afer coding & testing process |
| Effort | Person. Months | During Initial Plan |
| Estimated Working Time | Person. Hours/day | During Initial Plan and SPMP |
| Reviewed Results and Status | Hours | After Review Meetings |
| Requirements Stability | Relativeness of System Functionalities | After testing |
| Defects | Error/LOC | After testing |
| Resource Cost | % Assigned task/ total task | During SPMP |
| Risk Probability | Percentage (%) | Once a week |
| Remaining Work | Hour | Once a week |
| Work complete | Percentage (%) | Once a week |
| Duration | Day | Once a week |
| Work | Hour | Once a week |
| Cost | Person. Hours/day | During Initial Plan and SPMP |

Table 54 : Metrics Collection

## Risk management plan

Risk assingments:

In this project there will be a lot of problems to be faced in. These problems are scheduling,programming and misunderstand user requirements and health problems.

Scheduling problems:

During project, all group members will learn new tools and learn standards and this will take time therefore, we have a timing problem to submit documentation on death line.

In this semester, all the project members have a lot courses therefore, we have a timing problem to finish our documents according to due date.

Programming problems:

Lack of skill knowledge tools will be created while doing our project. It means that group member does not have any knowledge about tools. Group members will decide to select appropriate tool by using updated dnowledge of tools.

Misunderstand user requirements:

User requirements are the most important things that improve the quality of a product. In user requirements, we have to satisfy customer needs.In order to improve the process we have to understand user requirements better.Misunderstand the user requirements is a problem for a project. Misundertanding user requirements lead to wrong implementation of a project.

Health problems:

Our project has a specific tasks, and we have to do these tasks step by step. If one group member is ill, process of the project is not improved because of the lack of group member.

## Project closeout plan

For the main event of the Closeout Plan is to review if all of the features of the software product ensures all of the customer requirements. To do that, the project group will be meeting on a scheduled date after the implementation phase. Mainly the Test Team and also the other members will be testing the software product over and over again until all the team member satisfies for the product.

Another main event of the Closeout Plan is to archive all of the reports that have created during the software product creation. These archives will be a data CD or/and a data DVD. These files will be archived as hard copies as well to make the software product more traceable and easier to understand for other software engineers that will be dealing with the product after the installation.

# Technical process plans

The Technical Process of project shall specify the development process model, the technical methods, tools and techniques to be used to develop work products. In addition, technical process shall involve planning to establishing process, continuing project infrastructure and product acceptance plan.

## Process model

The process model helps to indicate representing of the relationships among major project work activities and supporting processes which are specifying the flow of information and work products among activities and functions. In detail, the process model of the project involves; reviews to be conducted, major milestones to be achieved, project deliverables to be completed .In addition, the process model of the project includes project initiation and project termination activities. Therefore, the group members of this project are decided to use a v-model development lifecycle and also the schedule of the project is predefined by the acquirer.

Figure 3 : Process Model

The architecture of The V-Model

Tool Requirements

Methods

Procedure

Software Development

Quality Assurance

Configuration Management

Project Management

V-Model is the standard of the individual standardization levels implement the following situations:

1. Procedure ("What has to be done?")

2. Methods ("How is this to be achieved?")

3. Tool Requirements ("What is used to do something?”)

At the all levels the standards are structured according to the areas functionality. These areas of functionality are called submodels: Project Management (PM), Software Development (SD), Quality Assurance (QA), Configuration Management (CM). These four submodels are closely interconnected and mutually influence one another by exchange of products or results. Using V-Model process model in this project mainly, it contains information on the project development, difficulties and problems. It also contains information on how these difficulties and problems to be handled. In addition, it involves general data dictionary in terms of definition for organization which are benefits both projects and organizations from it. It is used to be implemented and updated during to project.

## Methods, tools, and techniques

In this phase of this document is to specify the development methodologies, programming languages, tools and techniques to be used to specify, design, build, test, integrate, document, deliver, modify and also maintaining the project deliverables which known as work products.

In Web_based Tracking System for CTIS Alumni (*) uses an object-oriented design methodogy based on UML which known as Unified Modeling Language. In this project, .NET Framework will be implemented in the development of the software and also C# will be used as coding language. Microsoft Visual Studio will be used for user graphical interfaces and will be used Sybase Power Designer for database designing. In addition, MySQL will be used managing the CTIS student’s information as database management system and also documents are prepared by using MS Word 2003 and MS Project 2003. It is the well-known fact that team members have more than one role and responsibilities in the project so every documents must be acceptance by every team members before giving the customer (*). On the other hand, project documentation is available on the team web site so customer easily will reach the documents about individual project. The other important fact that acceptance test will be done by the CTIS department who responsible senior project’s staff. Testing is the most important part of improving project deliverable and non-deliverable work products in terms of quality so test scenarios will be created by team members. Therefore, test cases will be created from these test scenarios and they should be applied in it. In addition, reports and procedures will be created because of fixing bugs or modification of the work products shall be specified.

Technical standards, policies and procedures for documentation will be  IEEE Std. 1058-1998, IEEE Standard for Software Project Management Plans [1]; IEEE Std. 830-1998, IEEE Recommended Practice for Software Requirements Specifications [2]; IEEE Std. 1063-1998,IEEE Standard for Software User Documentation[3] will be used.

## Infrastructure plan

In this phase of this document is to specify the plan for establishing and maintaining the development environment which is included hardware, operating system, network, and software. Also applying standards and procedures will be conducted the project. In our project, there are four laptops computers, which are Mobile Centrino and Pentium IV processors, running on Windows XP and Windows Vista operating system. In the project, star topology is preferred as a network topology that applying in our local area network which is setup. In addition, MS Word 2003, MS Project 2003, Sybase Power Designer, My SQL Database, Microsoft Visual Studio 2008, .NET Framework, Fire Fox, Internet Explorer software will be used for documentation, design, implementation, testing and project management.

The other important fact that provisions for physical security is doing project in team member’s home or library. In office space or team member’s room should be included four 1.50cm x 60 cm table and four seats are needed and also should be supplied food& beverage in five hour intervals generally. It is the most crucial fact that administrative personnel should be experienced and be knew little technical and managerial knowledge in project management. Also Janitorial services should be given daily.

## Product acceptance plan

In this phase of this document is to specify the plan for acquirer acceptance of the deliverable work products generated by the project and acceptability of deliverable work products should be specified in this plan. Therefore, at the end of every milestones of project will be signed-off and the acquirer, who name is Beyhan Akporay, will have to review blueprint of documentations and components. In addition, V Model is the upgraded version of the waterfall model so sign-off won’t be waited for the next step for project for starting next phase of SDLC. After sign-off process will be finished in documentation and components, necessary changes will be reviewed by team members and will be updated.

The determining acceptability of product acceptance tests shall be applied and signed by the acquirer according to formal agreement of acceptance criteria which is SRS document of Web-based Tracking System CTIS Alumni. In addition, software requirements specification is the document referring to which test team develops their user acceptance test cases and test scenarios. Therefore, the final product will be corresponded the SRS which all items about product is included and also the acceptability of the final product will be conformed to product acceptance test.

# Supporting process plans

The Requirements baseline is maintained in the SRS document; it defines the required functional, performance, and operational characteristics of the system. The Production baseline includes the delivered software, data, and system documentation.

## Configuration management plan

- Configuration Identification:

Problems identified during system integration and test, and resolved prior to delivery of the system to operations, are handled by the development and test teams as Problem Reports. Also there may be other reports sent by the acquirer. These change reports handled by the Configuration Management Team as well.

- Configuration Documentation:

Errors found during system integration and test, should be documented by the Configuration Management Team and should be reported to the development team. All of the error reports, change requests and correction reports will be documented and archived for prior reports and problems.

- Configuration Status Accounting:

Configuration status accounting involves the recording and reporting of the change process.  The goal of configuration status accounting is to maintain a status record of all items in the system, thus providing traceability of all changes to the network. Configuration status information will be recorded and maintained in a centralized repository; most typically some sort of archive.

- Baseline Changes:

Implementation for the new or changed requirement is tracked along with all other requirements.  After the new requirement is approved and documented, the requirements analysis team generates configuration change requests to implement the change.

## Verification and Validation

The verification and validation for the software project in SPMP, it shall describe the organizational relationships between development activities and verification and validation activities and also this plan verifies and validates the software product which meets the user requirements. In addition, it shall involve schedule, scope, resources, responsibilities, tools, techniques, and methodologies to be performed the verification and validation work activities orderly. It is the most important fact that verification is mostly used for end-user products. On the other hand, validation is evaluated for each stage of software development. In detail, after the development process will be ended, validation of the Web-based tracking system shall be evaluated every development phase of project by the lead tester who names is E.Bengü Karakoç, M.Burçak Aydın. The verification progress of software project shall be evaluated related modules which is operated run test for fixing errors and bugs of modules. In addition, when applying the run test, test engineers shall be prepared the test case of modules. It is the undeniable fact that by the help of verification and validation helps to increase the quality of the software product.

It is most important fact that developing project of deadlines of project deliverables is represented as milestones of verification and validation. These milestones, which are completed, shall be indicated to the acquirer for validation purposes. In addition, these deliverables shall be reviewed by V&V team in the scheduled meeting with the acquirer and also shall be meet a need for acquirer and also specification.

After each prototype shall be prepared by development team and shall be tested by V&V team members, these prototypes shall be indicated to the acquirer. In addition, the project manager who name is E.Bengi Karakoç shall be controlled the final product, which known as a milestone, after team a member evaluates. Not only project managers shall monitor the verification and validation but also quality managers shall monitor the verification and validation. At the end of demonstration of validation, user acceptance and system validation shall be checked.

## Documentation Plan

This section of the document defines the documentation plan, documents to be delivered and created. The table below shows the due dates and the acquirers of the project deliverables as documentation form. All of the documents have given and will be given before the due date to reduce the communication disunity. All of the documents are created and will be created within the format given by the acquirer and the CTIS department. The documents are prepared by the all the members of the project group but some of the format necessities and other obligation are determined by the documentation team.

| Product: | Delivery Information: |
| --- | --- |
| Initial Plan: | The initial plan of the project is going to be prepared until October 17th, 2008 and submitted to the project manager Beyhan Akporay. |
| Software Requirement Specification(SRS): | The Software Requirements Specification (SRS) document will be prepared on October 31st, 2008 and submitted to the senior project manager Beyhan Akporay. |
| Software Project Management Plan(SPMP): | The Software Project Management Plan (SPMP), which is controlling documents and planning and organizing the software project, is going to be prepared on November 28th, 2008 and submitted to Beyhan Akporay. |
| Software Design Document(SDD): | The Software Design Document (SDD) is a description of software which will be prepared on December 23rd, 2008 to Beyhan Akporay. |

Some other document that will be delivered is the Error Report Template Document. This document will be formatted as some sort of a fill-in-the-blanks sheet. After the installation, the customer will be able to fill this form on-line or a hard copy version and send it to the person who is responsible for the configuration management. Also, there will be some documents to be archived that are written in the meetings with the acquirer. These writing will be in some of the group members’ handwriting but if the group or the acquirer desires, these writings can be sent as e-mail for can be faxed.

## Quality Assurance Plan

The Software Quality Assurance Plan is to ensure software project for the supporting plan, standards, and procedures that software process and the software product shall be meet requirements specification.

The Software Quality Assurance Plan (SQAP) is to implement effectively quality assurance functions such as analysis, standards, audits, inspections, testing, and reviews for the Web-based Tracking System for CTIS Alumni in terms of the goals, processed, and responsibilities. The primary objective of SQA is to ensure the production high-quality of work products which is fit for requirements and implemented standards. During the each stage of the software life cycle, SQA provides to carry formal process of improving the quality of work products which is produced. Therefore, it is the well-known fact that the most important methods are Verification and Validation (V&V), Configuration Management (CM), Reviews and Audits (RA).

The System of quality assurance teams shall be responsible for ensuring to check source code, database structure, user manuals, and software integration system according to Quality Assurance issues. In addition, quality assurance team shall be ensured previous problems which won’t be occurred again and also these problems are well-designed documented. Therefore, quality assurance manager shall responsible assuring all quality standards which is applied in current project.

Reviews will be performed each week by the project manager for checking problems and then try to result solution. It is the well-known fact that reviews and audit plan help to create effective communication to improve solutions to problems so the quality of project also will be improved. Review & Audit process are explained in 7.5 Review & Audit Plan.

Quality Assurance Items shown below:

| Document | Reviewer(s) |
| --- | --- |
| Review Initial Plan | Beyhan Akporay |
| Review SRS | Beyhan Akporay |
| Review SPMP | Beyhan Akporay |
| Review SDD | Beyhan Akporay |
| User Manual | Beyhan Akporay |
| Review Unit Testing | Quality Assurance Team Members |
| Review Integration Testing | Quality Assurance Team Members |
| Review System Testing | Quality Assurance Team Members |

Table 55 : Quality Assurance Items

## Review and audits plan

One time a week, the project group has a scheduled meeting with the acquirer. In that meetin the acquirer declares the changes that needed t be done and the group is documenting the major and minor features that have been talked in the meeting. The documentation format is explained in the 7.3 of the SPMP document. There are non-scheduled meetings with the acquirer as well. These meetings will be at least one time a week at most 4-5 times a week.

One time a week, the project group has a scheduled meeting to review the changes that needed to be done in the system. These meetings are rarely documented because the group will be doing these changes right after the reviews. There are non-scheduled meetings as well and these meetings will be at least one time a week at most 6-7 times a week.

## Problem resolution plan

The main procedure to be followed when one of the project group members faces a problem is the basic configuration management procedure. The procedure below defines the basic procedure to be followed during the implementation of the project.

That is;

- First, be sure that all of the possible alternatives of that error or problem have been tried out before reporting the problem.

- Second, fill out the problem or error reporting form.

- Third, report it to the configuration team.

- Fourth, the configuration team analyzes the given problem and searches for alternative solutions.

- If the problem can be solved within the project group;

  - Configuration team sends the new requirements and problem solution to the Coding team.

  - Configuration team sends the problem report and the analyze report to the documentation team.

  - Coding team specifies the given solution and applies it on the project code.

  - Coding team send the solution document to the documentation team.

  - Documentation team archives all of the documents mentioned above in the same format from the beginning of the project until the end of the project.

- If the problem cannot be solved within the project group;

  - Configuration team searches new resources to find the solution for the specific problem.

  - If the configuration team finds the desired solution for the specific problem, the team continues from the standard procedure.

  - If the configuration team cannot find the desired solution for the specific problem, the team members should consult a CTIS instructor to understand, analyze and solve the given problem.

    - After then the project group continues from the standard procedure.

## Subcontractor management plans

N/A

## Process improvement plan

The process improvement for the project will be helped to understanding processes which is used to improve the quality of product and reduce the cost of product. It is the well-known fact that focusing error reduction to help improving the quality of product. The achieving successful process improvement activities are analyzing the processes, measuring the processes and changing the processes. Therefore, the quality of products depends on the development processes of the project in term of satisfying acquirer requirements in the review meetings. After at these review meetings, project team members shall be used several quality tools such as flowchart, check sheets, cause & effect diagram (Fishbone), pareto chart for solving problems. In addition, the documentation, bug lists, and tests conducted during the project will be consulted to determine if any improvements should be made.  If improvements are to be made, the procedures outlined in the Problem Resolution Plan (section 7.6 of this document) will be used.

# Appendices

## Appendix A

Figure 4 : Gantt Chart-1

## Appendix B

Figure 5 : Gantt Chart-2